## ProjectTeam
Name	GitHub Alias	Rolle
Christian Kocher	@christiankocher7	DV
Fabio Caggiano	@jmpout	DV
Marc Häsler	@haelser	SM
Marius Schär	@martyschaer	DV
Severin Kaderli	@severinkaderli	DV
Jürgen Vogel	@vgj1	PO
Urs Künzler	@UrsKuenzler	PO

## Product_Backlog
ID	Story Name	Description	Priority	Effort Plan Original [h]	Effort Plan Updated	Effort Actual	Status
1	Medication Reminders	Patient will be reminded to take their medication	1	30	22	36	In progress
2	Patient-Therapist Communication	Patient can talk to their therapist quickly and asynchronously	3	30		3	In progress
3	Mood Diary	Patient can record their mood, activity, sleep and food for any given date and share this information with their therapist.	1	30	21	22	In progress
4	Emergency Contacts	The patient has quick access to a number of emergency contacts, such as: A suicide hotline, their therapist, some close family members. It should be obvious how to reach the emergency contacts from any point in the application	2	4			In progress
5	Login	The patient can log in securely. Account creation is handled by the therapist.	1	4	10	13	In progress
6	Configure Persistency	The developers should be able to persist objects in an RDBMS	1	4	6	2	Done
7	Task 8	Persistence	1	2		2	Done
8	Task 9	Presentation	1	4			In progress

## Sprint_Backlog
ID	Sprint	Name	Description	Owner	Reviewer	Priority	Effort Plan Original	Effort Plan Updated	Effort Actual	Status
1.1	1	Model	Create the necessary model for the reminders	MS	CK	1	2		4	done
1.2	1	Database	Create database schema and mapping for the reminders	MS	CK	1	2	4	4	done
1.3	1	Scheduler	Scheduler which knows about the current reminders and schedules new ones	MH	MS	2	4		6	done
1.4	1	GUI	The user can see the reminders	CK	MH	1	4	6	6	in progress
1.5	1	Done Check	The user can check off a reminder	CK	MH	2	2		2	in progress
1.6	1	Defer	The user can defer a reminder	CK	MS	2	2		2	in progress
1.7	1	System Defer	The system can defer a reminder	CK	MS	3	2		4	waiting
3.1	1	Model	Create necessary model for the mood diary	SK	FC	1	2		2	done
3.2	1	Database	Create database schema and mapping for the mood diary	SK	FC	1	2	4	4	done
3.3	1	GUI - Mood	The user can choose his/her actual mood with a mood scale	SK	FC	1	4		5	done
3.4	1	GUI - Sleep	The user can enter how many hours he/she slept last night in hours	MH	SK	2	1		1	in progress
3.5	1	GUI - Water/Food	The user can create a list with detailed entries of his consumation for food and drinks	FC	CK	1	4			waiting
3.6	1	GUI - Medication	The User can write which medication he/she took today	MH	CK	1	4		1	in progress
3.7	1	GUI - Activites/exercises	The User can enter activities or exercises which he has done today	CK	MH	2	1			waiting
3.8	1	GUI - General Things	The User has the possibility to note any other important things into the mood diary	MH	SK	3	1		1	in progress
5.1	1	Login	The patient can open the pms with a login and mange his User	FC	MS	1	4	5	5	in progress
6.1	1	Configure JDBC	Configure JDBC connection	MS	SK	1	2	3	1	done
6.2	1	Configure Hibernate	Configure Hibernate for actual usage	MS	SK	1	2	3	1	done

1.4	2	GUI	The user can see the reminders	CK	MH	1	2		2	done
1.5	2	Done Check	The user can check off a reminder	CK	MH	2	2		2	in progress
1.6	2	Defer	The user can defer a reminder	CK	MS	2	2		2	in progress
1.7	2	System Defer	The system can defer a reminder	CK	MS	3	2		2	in progress
3.4	2	GUI - Sleep	The user can enter how many hours he/she slept last night in hours	MH	SK	2	2		1	done
3.5	2	GUI - Water/Food	The user can create a list with detailed entries of his consumation for food and drinks	FC	CK	1	4		4	done
3.6	2	GUI - Medication	The User can write which medication he/she took today	MH	CK	1	2		1	done
3.7	2	GUI - Activites/exercises	The User can enter activities or exercises which he has done today	CK	MH	2	1		1	done
3.8	2	GUI - General Things	The User has the possibility to note any other important things into the mood diary	MH	SK	3	1		1	done
5.1	2	Login	The patient can open the pms with a login and mange his User	FC	MS	1	6		8	in review
6.3	2	Persistence	The developer can checkout the repository and a database with sample data is created.	SK	MS	2	6	8	8	done
4.1	2	GUI	The user can see all important emergency contacts on a persistence part of the GUI.	MH	SK	2	4		0	waiting
2.1	2	Instant Messaging Communication Backend	The user can get in contact with his therapist and other patients.	MS	SK	3	6		3	in progress
7.1	2	Update Class Diagram		MS	MH	1	2		2	done

1.5	3	Done Check	The user can check off a reminder	CK	MH	2				in progress
1.6	3	Defer	The user can defer a reminder	CK	MS	2				in progress
1.7	3	System Defer	The system can defer a reminder	CK	MS	2				in progress
5.1	3	Login	The patient can open the pms with a login and mange his User	FC	MS	6				in review
4.1	3	GUI	The user can see all important emergency contacts on a persistence part of the GUI.	MH	SK	2				waiting
2.1	3	Instant Messaging Communication Backend	The user can get in contact with his therapist and other patients.	MS	SK	4				in progress
8.1	3	Final Presentation	All stakeholders have a clear idea of how far the project is, what still needs to be done and what experiences were made.	MH	all	4				in progress
2.2	3	Chat integration	The user can chat with other users.	MS	CK	4				in progress
5.2	3	Access rights	The user can only see the data applicable to himself	SK	FC	4				waiting

## BurndownChart
Sprint	Time of Record	Remaining Effort	Remaining Ressources
1	9.15.2015	200	200
1	9.16.2015	190	180